## User Stories
Epic 1 | Environment configuration
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 2](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/2) | USER STORY : Set up GiHub repository | As a Developer, I need to set-up a repository on GitHub platform to be able to have control over versions of project. | Working GitHub repository. | Not Applicable | [1861fb4](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/1861fb476f7bddef5536c8cea1f3afc96ba70731) | PASS
[# 3](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/3) | USER STORY : Set up dependencies | As a Developer, I need to register and obtain links for third party services. | All links of third party services (DB, mail provider, AWS) are obtianed and services set | Not Applicable | [76e4e21](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/76e4e21c9676bfe20584fc6a3b10795d0e40dca9) | PASS
[# 4](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/4) | USER STORY : Create working Django app | As a Developer, I need to install all dependencies, correctly set settings.py and create working app in local environment. | All dependencies are installed, settings.py all set for local view and when project is ran locally, symbol of correctly set app is shown (rocket). | Not Applicable | [c8d2a30](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/c8d2a30d6146cf84f0711ad5bdcd3c6ede959b02) | PASS
[# 5](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/5) | USER STORY : Deploy to Heroku | As a Developer I need to create a working Heroku deployement. | Working Heroku Deployment, when first deployed site accesed, it gives hint of correctly installed Django App (DEBUG = True). Create if statement in settings.py for DEBUG = False when deployed. | Not Applicable | [c8d2a30](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/c8d2a30d6146cf84f0711ad5bdcd3c6ede959b02) | PASS
Epic 2 | Database Models
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 7](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/7) | USER STORY : Define Database Schema | As a Developer, I need to create databse schema that fits the purpose of the project and also create all the modular apps that will be used in the project. | All Django apps are created and database schema in place to adhere to. | *( appendix 90 )* | [1d2929d](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/1d2929d2a31e281b2890acd9827199d2101d7811) | PASS
[# 8](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/8) | USER STORY : Create database realtionships | As a Developer, I need to define relatinships between models and import the relationships into working apps models. | All models are working with the relationships defined, all models that are related to other app models are linked via import statements. | *( appendix 91 )* | [1d2929d](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/1d2929d2a31e281b2890acd9827199d2101d7811) | PASS
[# 9](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/9) | USER STORY : Implement Data Validation in Models | As a Developer, I need implement data validation rules within Ohm-Azing Components database models. | All values inserted into database are the correct values and types, all applicable fileds are all set to be required or/and to be unique or/and nullable/not nullable. | *( appendix 92 )* | [1d2929d](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/1d2929d2a31e281b2890acd9827199d2101d7811) | PASS
Epic 3 | User Authentication and Authorisation
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 11](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/11) | USER STORY : Implement user registration | As a Site User I am able to register to create new account and to select username and passsword. | Not registered user : When I visit the site then I am able to register, select free username and create valid password. | *( appendix 93 )* | [5a19fd0](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/5a19fd0b165c1ddda2e5cee6dc27f62fb5d4c213) | PASS
[# 12](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/12) | USER STORY : Log In | As a Site User I am able to Log In to see registered user section. | 1.Registered user : When I visit the site then I am able to login via login link. 2.Not registered user : When I visit the site and trying to log in then I am given error message that user does not exist. | *( appendix 94 )* | [5a19fd0](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/5a19fd0b165c1ddda2e5cee6dc27f62fb5d4c213) | PASS
[# 13](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/13) | USER-STORY : Reset my password if forgotten | As a Site User I am able to Reset My Password to change my password if forgotten. | When I visit login page then I have the option to reset my password via provided link and email with reset link is sent to me. | *( appendix 95 )* | [5a19fd0](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/5a19fd0b165c1ddda2e5cee6dc27f62fb5d4c213) | PASS
[# 14](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/14) | USER STORY : Log out | As a Site User, I am able to log out to leave the site functions for registered users. | 1.Registered user : When I am logged in then I am able to logout. 2.Not registered user : Don't have that option. | *( appendix 96 )* | [5a19fd0](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/5a19fd0b165c1ddda2e5cee6dc27f62fb5d4c213) | PASS
Epic 4 | Custom Admin Interface
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 16](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/16) | USER STORY : Categories section | As a Business Owner, I have option to do full CRUD with item categories in order to manage my shop. | Staff/SuperUser : When I log in with my credentials then I am able to navigate to admin tools section to perform CRUD on shop categories. Users with no staff or Superuser rank : Not able to access that functinality. | *( appendix 97 )* | [7750783](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/7750783f78551c3a812957ce6be6d23397cf471a) | PASS
[# 17](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/17) | USER STORY : Items section | As a Business Owner, I have option to do full CRUD with items in order to manage products sold in my shop. | Staff/SuperUser : When I log in with my credentials then I am able to navigate to admin tools section to perform CRUD on shop items. Users with no staff or Superuser rank : Not able to access that functinality. | *( appendix 98 )* | [bd40bbf](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/bd40bbfb7c2625bfb3903df6d746aaf481804568) | PASS
[# 18](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/18) | USER STORY : Invoices section | As a Business Owner, I have option to view or download any invoice that was created by shoppers. | Staff/SuperUser : When I log in with my credentials then I am able to navigate to admin tools section to view and download invoices. Users with no staff or Superuser rank : Not able to access that functinality. | *( appendix 99 )* | [d041060](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/d0410601e36811992c9b0ff2b22db3646872a917) | PASS
[# 19](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/19) | USER STORY : Vouchers section | As a Business Owner, I have option to perform full CRUD on "Vouchers" that could be redeemed via checkout. | Staff/SuperUser : When I log in with my credentials then I am able to navigate to admin tools section to create, read, edit and delete "vouchers" redeemable at the end of checkout process. Users with no staff or Superuser rank : Not able to access that functinality. | *( appendix 100 )* | [d5601e6](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/d5601e6a80130048d2d3533f3cde2a7172d47b62) | PASS
[# 20](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/20) | USER STORY : Comments section | As a Business Owner, I have option to approve/delete comments to ensure no inapproproate content on the project page. | Staff/SuperUser : When I log in with my credentials then I am able to navigate to admin tools section approve/delete comments. Users with no staff or Superuser rank : Not able to access that functinality. | *( appendix 101 )* | [797af69](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/797af69ea601041f30210b958552650628bdd9b7) | PASS
[# 21](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/21) | USER STORY : Postage Settings section | As a Business Owner, I have option to adjust free postage treshold and posatege fees for standad and express delivery options. | Staff/SuperUser : When I log in with my credentials then I am able to navigate to admin tools section to change postage settings. Users with no staff or Superuser rank : Not able to access that functinality. | *( appendix 102 )* | [1630d1f](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/1630d1f149919cf27264831bdeee4283c2e05902) | PASS
[# 28](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/28) | USER STORY : Email interface for marketing purposes | As a Site admin, I need to implement Mailing interface to be able to send emails to all users signed up for email communication. | Staff/SuperUser : When I log in with my credentials then I am able to navigate to admin tools section to to create drafts/send emails to all users that are signed up to receive email newsletter. Users with no staff or Superuser rank : Not able to access that functinality. | *( appendix 103 )* | [c05fbef](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/c05fbefce9cd3214b232a4df6eefb26d31efd5e4) | PASS
[# 97](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/97) | USER STORY : Postage label printing | As a Site Admin, I need implement postage label printing page to be able to Effortlessly print postage labels. | When I log in as Superuser and navigate to Admin Tools then I can select order to view and print postage label based on order details. | Won't be implemented - Marked as "Won't Have" on Kanban Board | N/A | N/A
[# 98](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/98) | USER STORY : Order status emails | As a Site Admin, I can mark orders as accepted, pending, fulfilled to be able to keep customers informed of the status of their order. | When I navigate to Admin Tools and Invoices then I can see status of the order and I can change the status, customer is then notified via email of the progress. | Won't be implemented - Marked as "Won't Have" on Kanban Board | N/A | N/A
Epic 5 | General Features
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 23](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/23) | USER STORY : FavIcon & Title | As a Site User I woul like to be able to differenciate this site from other sites opened in my browser, in order of easy navigation. | When I navogate to the site, then I am clarly served with FavIcon and title of the site . | *( appendix 104 )* | [8f235c7](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/8f235c7c3e6871b1f19ee4d28bcebeae9bc41171) | PASS
[# 24](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/24) | USER STORY : Header | As a Site User I want to be able to navigate easily through-out the site. | When I navigate to the site, I am able to see header with logo and icons for menu, vault and wishlist (if logged in). | *( appendix 105 )* | [5a19fd0](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/5a19fd0b165c1ddda2e5cee6dc27f62fb5d4c213) | PASS
[# 25](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/25) | USER STORY : Footer | As a Site User I want to be able to find useful info on the bottom of the site in order not to scroll and search too much around. | When I navigate to the site, I am able to see footer with basic contact details, link to socials and accepted payment options. | *( appendix 106 )* | [5a19fd0](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/5a19fd0b165c1ddda2e5cee6dc27f62fb5d4c213) | PASS
[# 26](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/26) | USER STORY : Loader | As a Site User I want to be able to see if page is working in the form of loader that appears when complex task is performed. | When I navigate throughout the site when complex actions are being submitted (DB) then the loader appears to ensure me the site didn't freeze. | *( appendix 107 )* | [15a14bd](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/15a14bdcd9066bf13f0a9b1428debed0d879834a) | PASS
[# 27](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/27) | USER STORY : Toasts | As a Site User I want to be informed of results of requests performed in the form of toast that appears when complex task is done sucessfully / unsuccessfully. | When I navigate throughout the site when complex actions are being submitted (DB) then the toast appears to inform me of the result of action. | *( appendix 108 )* | [be40cc1](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/be40cc1431dc1394c6d53423c605bd844daa3fb7) | PASS
Epic 6 | User Profile Management
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 31](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/31) | USER STORY : Change Details (Phone Number, Email Address, etc.) | As a Site User I can Update My Details to be able to manage my account in case of changes. | Logged in user : When I login then I can clearly navigate to "My Details" section where I can change my details. Not logged in user : Don't have that option as not logged in. | *( appendix 109 )* | [608f056](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/608f0564333f5a55de3af447b3e0666e4ea4fe0a) | PASS
[# 32](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/32) | USER STORY : Delete my account | As a Site User I can Delete My Account to be able to opt out from all services. | Logged in user : When I navigate to "my details" then I have the option of delete my account entirely. Not logged in user : Don't have that option as not logged in. | *( appendix 110 )* | [608f056](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/608f0564333f5a55de3af447b3e0666e4ea4fe0a) | PASS
[# 33](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/33) | USER STORY : Profile Picture | As a Site User I can Change my profile picture to add the finishing touch to my profile. | Logged in user : When I navigate to "My Details" section then I change my profile picture. Not logged in user : Don't have that option as not logged in. | *( appendix 111 )* | [a7bd28a](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/a7bd28a7539cde8d158c8c3a8f95a51aeda3caec) | PASS
[# 34](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/34) | USER STORY : Opt In/Out for Newsletter | As a Site User I can Opt In/Out for Newsletter or other marketing communtiation to be able to change my preferences. | Logged in user : When I navigate to "My Details" section then I can mark/unmark to receive marketing emails, sms or phone calls. Not logged in user : Don't have that option as not logged in. | *( appendix 112 )* | [a7bd28a](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/a7bd28a7539cde8d158c8c3a8f95a51aeda3caec) | PASS
Epic 7 | The Shop
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 36](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/36) | USER STORY : Shop Highlights | As a Site User, I would like to See Newest and Favourites on the landing page so I can see easily what products are after arriving and what are most popular. | When I navigate to the site then on landing page I can see featured products, free delivery treshold. | *( appendix 113 )* | [94932b4](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/94932b44ceee72c1dccff795eab32b6a73bdea0d) | PASS
[# 37](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/37) | USER STORY : Shop by Category | As a Site User, I would like to have the shop items sorted by category so I can browse the items faster. | When I visit the shop with all items then I can see all the categories displayed and when category clicked, items belonging to the category will display. | *( appendix 114 )* | [5081a8f](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/5081a8f7ec7c4d8886ccbaeb15f77cf5ddc5635a) | PASS
[# 38](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/38) | USER STORY : Product Details | As a Site User, I would like to see the details of each item in separate page so I won't get lost in too much info. | When I visit the shop with all items and open details of certain item then I can see all the relevant info per item. | *( appendix 115 )* | [765f8ad](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/765f8ad074062865599a148bbb882fddb095acd5) | PASS
[# 39](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/39) | USER STORY : Add to Vault | As a Site User, I need to be able to add items to vault in order to see the entire order before payment. | When I click "Add to vault" button then the item adds to vault. | *( appendix 116 )* | [06cf6d4](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/06cf6d49910a33306c951d4963dcee42c95d6ee5) | PASS
[# 40](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/40) | USER STORY : Add to Wishlist | As a Site User, I need to be able to add items to my Wishlist in order to see keep the items I am interested in separately. | Logged in User : When I click "Add to Wishlist" toggle then the item toggles in Wishlist. Not Logged in User : Doesn't have that option. | *( appendix 117 )* | [618624a](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/618624a73180d51eaeb62a656790f0b295726df1) | PASS
[# 41](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/41) | USER STORY : Comment on Products | As a Site User I can Comment on Items to share my opinion. | Logged in user : When I navigate to item detail in shop then I am able to add comment on the relevant item. Not logged in user : Doesn't have that option. | *( appendix 118 )* | [aaacdb9](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/aaacdb93817745397d28e8b3cd63dcafe8162939) | PASS
[# 42](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/42) | USER STORY : See Comments of Others | As a Site User I can see other comments on Items to read other Users opinions. | Logged in user : When I open item detail then I am able to see other people comments. Not logged in user : Doesn't have that option. | *( appendix 119 )* | [8c48498](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/8c484989ced1eb6a400534a8da2aadb6a89b4d98) | PASS
[# 72](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/72) | USER STORY : Like / Dislike Items of Shop | As a Site User I can Like / Dislike particular Item in Shopin order to express my opinion. | Logged in user : When I navigate to shop and open detail of Item then I am able to like or dislike the Item. Not logged in user : Doesn't have that option. | *( appendix 117 )* | [35a4884](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/35a48849bb86b7ace9b376d3d8e645dc4954d472) | PASS
[# 99](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/99) | USER STORY : Frequently bought together | As a Site User, I can see what items are bought together to be able to what else can I buy for the same project. | When I navigate to the shop and item detail, I can see what items are frequenly bought with the item that I am viewing. | Won't be implemented - Marked as "Won't Have" on Kanban Board | N/A | N/A
Epic 8 | Wishlist
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 44](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/44) | USER STORY : Display Wishlist Items | As a Site User, I can display items in My Wishlist in order to manage the items. | Logged In User : When I log in and navigate to "My Wishlist" section then I can clearly see all items in the wishlist . Not Logged In User : Doesn't have that option. | *( appendix 120 )* | [b71e9f9](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/b71e9f93064e251ebca34ca52ecf6e4e2fa0e672) | PASS
[# 45](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/45) | USER STORY : Remove Items from Wishlist | As a Site User, I can remove items from My Wishlist one by one in order to manage the items in the Wishlist. | Logged In User : When I log in and navigate to "My Wishlist" section then I can clearly see an option to delete item from Wishlist . Not Logged In User : Doesn't have that option. | *( appendix 120 )* | [15910d7](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/15910d7bb677671a70b3253290957915f93002ab) | PASS
[# 46](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/46) | USER STORY : Clear Wishlist | As a Site User, I can delete all items in My Wishlist in order to manage the items. | Logged In User : When I log in and navigate to "My Wishlist" section then I can clearly see option to delete all items from the Wishlist . Not Logged In User : Doesn't have that option. | *( appendix 120 )* | [84e5561](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/84e55610bf98f797529552d0dfd6f5df50ecdcd2) | PASS
Epic 9 | Vault
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 48](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/48) | USER STORY : Display content of Vault | As a Site User, I can display items in Vault in order to manage the items. | When I visit the site and navigate to "Vault" section then I can clearly see all items in the Vault . | *( appendix 121 )* | [d407252](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/d40725233ee4938ac42d36a9a8505bf096f3e737) | PASS
[# 49](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/49) | USER STORY : Adjust amounts of items in Vault | As a Site User, I can adjust amount of each item in Vault in order to manage the items before proceeding to Checkout. | When I visit the site and navigate to "Vault" section then I can clearly see amount of each item and I have an option to adjust or remove the item from the Vault . | *( appendix 121 )* | [f90e353](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/f90e353901b79ed1e8083944ebcbf61716692e1d) | PASS
[# 50](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/50) | USER STORY : Clear the Vault | As a Site User, I can display items in Vault in order to manage the items. | When I visit the site and navigate to "Vault" section then I can clearly see all items in the Vault . | *( appendix 121 )* | [b0af0c3](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/b0af0c39015731013707ebca089e5854f4619573) | PASS
[# 51](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/51) | USER STORY : Proceed to Checkout | As a Site User, I can proceed to Checkout in order to pay for items in my Vault. | When I visit the site and navigate to "Vault" and I am happy with the content then I can clearly proceed to Checkout . | *( appendix 121 )* | [ea6f86e](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/ea6f86e2d27f280041f8d4c6b6deca2348392418) | PASS
[# 52](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/52) | USER STORY : Vault management toasts | As a Site User, I can see message that indicates Vault action along all items that are in Vault in order to be informed and have an idea what's in Vault without opening the Vault. | When I submit any "Vault" section action (add, delete, adjust) then I can clearly see in form of toast all items in the Vault, the total and postage treshold . | *( appendix 108 )* | [ea6f86e](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/ea6f86e2d27f280041f8d4c6b6deca2348392418) | PASS
Epic 10 | Checkout
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 61](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/61) | USER STORY : Checkout Page | As a Site User, I can see checkout page so I know exactly what am I being charged for. | When I add my desired products into Vault and click "secure Payment" then a payment page loads up. | *( appendix 122 )* | [8b3724a](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/8b3724a2ab7034874a20588ff9ca25fa3bd12cca) | PASS
[# 54](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/54) | USER STORY : Shipping Details | As a Site User, I can provide shipping details in order to inform the shop where to send my purchase. | Loged In User : When I navigate to "Secure Checkout" then I can enter / change (if provided in "My Details") shippings details . Not Loged In User : When I navigate to "Secure Checkout" then I can enter shippings details . | *( appendix 123 )* | [bbe7628](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/bbe7628cc0bcf618ba307c8b9084157e08c34c7c) | PASS
[# 62](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/62) | USER STORY : Save info | As a Site User, I can save provided shipping info in order the form being prefilled with next order. | Loged In User : When I navigate to "Secure Checkout" and provide new / different shipping info then I have an option to save the details provided. Not Loged In User : Doesn't have that option. | *( appendix 124 )* | [9c34d7d](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/9c34d7d35134ff1e957e435e64d248ee09e8fb6d) | PASS
[# 63](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/63) | USER STORY : Delivery Options | As a Site User, I can choose between standard and express delivery in order to control the speed of delivery. | When I navigate to "Secure Checkout" then I can choose my preferred delivery option. | *( appendix 125 )* | [0ab3c1e](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/0ab3c1e6966f2454189670aa4ba0ec9e135e9544) | PASS
[# 57](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/57) | USER STORY : Payment | As a Site User, I have an option providing payment details in order to pay for my goods. | When I navigate to "Secure Checkout" and fill in all the required info then I can pay by providing payment media number. | *( appendix 122 )* | [0ab3c1e](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/0ab3c1e6966f2454189670aa4ba0ec9e135e9544) | PASS
[# 55](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/55) | USER STORY : Vouchers | As a Site User, I have an option to redeem dicount codes in order to get discount on my purchase. | When I navigate to "Secure Checkout" then I have an option to redeem dicount code in clear manner. | *( appendix 126 )* | [0fbac68](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/0fbac6828c0efd40a85cfc957e6787acdaf51aba) | PASS
[# 58](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/58) | USER STORY : Invoice Generator | As a Site Admin, I need to be able to generate invoice in *.pdf format in order the invoice being attached to the confirmation email. | When User sucessfully proceeds through checkout the invoice in *.pdf needs to be generated based on order details adn saved to database. | *( appendix 127 )* | [7395bb8](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/7395bb80231ab9d561153d54931fdd3fa7de11fe) | PASS
[# 59](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/59) | USER STORY : Confirmation Email | As a Site User, I do get confirmation email in order to know the transaction was sucessfull. | When I sucessfully proceed through payment, then I am notified via email about my purchase. | *( appendix 128 )* | [2b5929a](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/2b5929accb57289a57dd7a6deb64f81ecc04a228) | PASS
[# 60](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/60) | USER STORY : Stock Update | As a Site Admin, I need to be able to update stock amounts after every purchase in order the manage the inventory. | When User sucessfully proceeds through checkout then the amounts of stock levels are updated. | Not Applicable | [f901a9c](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/f901a9cf9609396bd325d29f2319e886f5536043) | PASS
[# 56](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/56) | USER STORY : Stripe and Webhooks Setup | As a Site Admin, I need to be able to process the order functions even in event of failure in order to ensure no paying customer is left without goods. | When User provides valid payment media number but connection is interrupted for some reason during the confirmation process then all other functions (saving order, email, invoice) needs to proceed as normal via webhooks. | Not Applicable | [9d07b91](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/9d07b912e0be257efa606122f476a791748ac300) | PASS
[# 64](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/64) | USER STORY : Success Page | As a Site User, I can clarly see sucess page in order to know my order went through without checking my emails. | When I sucessfully proceed with payment then I can see success page containing order details, order number and estimated delivery dates. | *( appendix 129 )* | [c7d638c](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/c7d638cc91c9e8cc931d036b574f4737b9b192e1) | PASS
Epic 11 | Order History
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 66](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/66) | USER STORY : Accessing Order History | As a Site User, I can access my own past orders in case of needing them in future. | Loged In User : When I navigate to "Order History" section then I clearly see all my past orders then . Not Loged in User : Doesn't have that option. | *( appendix 130 )* | [3b301fc](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/3b301fc1521ad8851a4392ab00337a54ac8a402e) | PASS
[# 67](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/67) | USER STORY : Viewing past invoices | As a Site User, I can view detail of any of my own past orders in case of needing them in future. | Loged In User : When I navigate to "Order History" and select partucular invoice to view then then the the invoice opens in new browser tab . Not Loged in User : Doesn't have that option. | *( appendix 131 )* | [3b301fc](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/3b301fc1521ad8851a4392ab00337a54ac8a402e) | PASS
[# 68](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/68) | USER STORY : Downloding past invoices | As a Site User, I can download any of my own past order invoices in case of needing them in future. | Loged In User : When I navigate to "Order History" and select partucular invoice to download then then the the invoice downloads in web browser . Not Loged in User : Doesn't have that option. | *( appendix 132 )* | [3b301fc](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/3b301fc1521ad8851a4392ab00337a54ac8a402e) | PASS
Epic 12 | Search Bar
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 70](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/70) | USER STORY : Search Bar in header of page | As a Site User I am able to use search function through Categories, Items and Item descriptionsin order to quickly find what am I looking for. | When I navigate to any page of the site then I can see the search bar located in the header. | *( appendix 133 )* | [93a786e](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/93a786e4d8c00f1b8cdf8754843cd3f83bdf2549) | PASS
[# 71](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/71) | USER STORY : Search results | As a Site User I can see search result to easily navigate through them. | When I submit search criteria and clcik the search button then I am able to see the results. | *( appendix 134 )* | [76022d3](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/76022d3c766485f452f85bab87b7588ee384f46b) | PASS
Epic 13 | Styling and design of UI
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 74](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/74) | USER STORY : Intuitive Navigation | As a Site Developer, I need to insure easy navigation throughout the site | When user does access the site then all links and actions are intuitive and don't need too much thinking, design is responsive on all device sizes. | Not Applicable | [5707b7b](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/5707b7b967861552ed18de3f89c954560dd2f623) | PASS
[# 75](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/75) | USER STORY : Color Scheme | As a Site Developer, I need to insure easy navigation throughout the sit | When user does access the site then all links and actions are intuitive and don't need too much thinking, design is responsive on all device sizes. | Not Applicable | [5707b7b](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/5707b7b967861552ed18de3f89c954560dd2f623) | PASS
[# 76](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/76) | USER STORY : W3C + WAVE Compatibility | As a Site Developer, I need to insure easy navigation throughout the site for users in need of ease of access | When user in need of ease of acces tools does access the site then all links and actions are labelled and intuitive and don't confuse the User. | Not Applicable | [2043e49](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/2043e497eef8b727f24fe90bf1f014b6756b9615) | PASS
Epic 14 | Testing and Validation
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 78](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/78) | W3C HTML validation | As a Site Developer, I need to ensure *.html files do pass the W3C validation. | When I access any site and inspect the source code then copy the source code to W3C validaor it doesn't display any major errors. | Not Applicable | [3df6e14](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/3df6e14e18d1af001b0681e040c32bb0a0838817) | PASS
[# 79](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/79) | W3C CSS validation | As a Site Developer, I need to ensure style.css file do pass the W3C validation. | When I copy and paste the content of style.css file then it doesn't throw any major errors. | Not Applicable | [d2f8a5a](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/d2f8a5af34e5447385796a73a270ea102f2314d0) | PASS
[# 80](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/80) | JS validation | As a Site Developer, I need to ensure *.js files do pass the JS Lint validation. | When I copy and paste the content of *.js files then it doesn't throw any major errors. | Not Applicable | [aa7b1ca](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/aa7b1ca0c5191d05575a69e381e3953c513a5526) | PASS
[# 81](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/81) | PEP8 validation | As a Site Developer, I need to ensure *.py file do pass the PEP8 validation. | When I copy and paste the content of *.py files then it doesn't throw any errors. | Not Applicable | [d8cf9ba](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/d8cf9babec03c031dc7dec4d960e453b9967d246) | PASS

## Responsivness
Directory | File | State | iPhone 8 * | Fold 4 * | Fire HD 8 * | Galaxy Tab S6 * | HD * | Full HD *
\checkout | checkout_ok.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\checkout | checkout.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\history | order_history.html | Only Logged in | PASS | PASS | PASS | PASS | PASS | PASS
\items | item_detail.html | Logged In | PASS | PASS | PASS | PASS | PASS | PASS
|  | Not Logged In | PASS | PASS | PASS | PASS | PASS | PASS
\items | shop.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\landing | index.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\landing | search_results.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\owner | categories.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | category_delete_confirm.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | comment_delete_confirm.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | comments_owner.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | edit_category.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | edit_email.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | edit_item.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | edit_voucher.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | email_delete_confirm.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | invoices.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | item_delete_confirm.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | items.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | new_category.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | new_email.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | new_item.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | new_voucher.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | newsletter_emails.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | owner.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | postage.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | voucher_delete_confirm.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\owner | vouchers.html | Only as SuperUser | PASS | PASS | PASS | PASS | PASS | PASS
\profilemanager | my_details.html | Only Logged in | PASS | PASS | PASS | PASS | PASS | PASS
\vault | vault.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\wishlist | wishlist.html | Only Logged in | PASS | PASS | PASS | PASS | PASS | PASS
\templates | 403.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\templates | 404.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\templates | 500.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\templates | base.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\templates | footer.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\templates | header.html | Logged In | PASS | PASS | PASS | PASS | PASS | PASS
\templates | header.html | Not Logged In | PASS | PASS | PASS | PASS | PASS | PASS
\templates\toasts | toast_error.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\templates\toasts | toast_info.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\templates\toasts | toast_success.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\templates\toasts | toast_vault.html | Not Applicable | PASS | PASS | PASS | PASS | PASS | PASS
\templates\account | `*.html` | Logged In | PASS | PASS | PASS | PASS | PASS | PASS
\templates\account | `*.html` | Logged Out | PASS | PASS | PASS | PASS | PASS | PASS

## Test Cases
PP5 Ohm-Azing Components
Test Case 001 - General Site Navigation - Not registered user
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Ohm-Azing Components page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Menu | Menu displayed | Worked as expected | PASS
3 | Click "Visit Shop" | Shop Page displayed | Worked as expected | PASS
4 | Select any category | Items options changed regrding selected category | Worked as expected | PASS
5 | Click on sorting criterion | Sorting options displayed | Worked as expected | PASS
6 | Select sorting option | Loader displayed | Worked as expected | PASS
|  | Items sorted re sorting criterion | Worked as expected | PASS
7 | Click on pagination criterion | Pagination options displayed | Worked as expected | PASS
8 | Select pagination option | Loader displayed | Worked as expected | PASS
|  | Items paginated re pagination criterion | Worked as expected | PASS
9 | Click on logo | Landing Page Displayed | Worked as expected | PASS
10 | Click on Menu | Menu displayed | Worked as expected | PASS
11 | Click "Register" | Registration Page displayed | Worked as expected | PASS
12 | Click on "Terms and Conditions" | Terms and Conditions Modal displayed | Worked as expected | PASS
13 | Click "Close" button | Modal closes | Worked as expected | PASS
14 | Click on "Privacy Policy" | Privacy Policy Modal displayed | Worked as expected | PASS
15 | Click "Close" button | Modal closes | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 002 - Search Function
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Ohm-Azing Components page | Landing Page Displayed | Worked as expected | PASS
2 | Click Search | Error message "empty field" Displayed | Worked as expected | PASS
3 | Fill In Search Term and click Search | Search Results Displayed | Worked as expected | PASS
4 | Click on Category in Searach Results | Shop Page opened | Worked as expected | PASS
|  | Category Selected | Worked as expected | PASS
5 | Fill In Search Term and click Search | Search Results Displayed | Worked as expected | PASS
6 | Click on Item in Search Results | Shop Page opened | Worked as expected | PASS
|  | Item Detail Displayed | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 003 - Registering New User
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Ohm-Azing Components page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Menu button | Menu displayed
3 | Click on Register | Register Form Displayed | Worked as expected | PASS
4 | Look fo register button | Register button initially hidden | Worked as expected | PASS
5 | Fill in form with correct credentials | Register button appears | Worked as expected | PASS
6 | Fill in password 1 and password 2 | Password hints and register button toggle | Worked as expected | PASS
7 | Click Terms and Conditions link | Modal with T&C's Displayed | Worked as expected | PASS
8 | Click Back button on Modal | Modal Closes | Worked as expected | PASS
9 | Click Privacy Policy link | Modal with Privacy Policy displayed | Worked as expected | PASS
10 | Click Back button on Modal | Modal Closes | Worked as expected | PASS
11 | Repeat process with username "tomas" | Error message "existing user" Displayed | Worked as expected | PASS
12 | Repeat process wit email "tkubancik@gmail.com" | Error message "existing user" Displayed | Worked as expected | PASS
13 | Repeat process with new credentials | Info about validation email sent displayed | Worked as expected | PASS
14 | Open your email provider and click the validating link | Confirmation form displayed | Worked as expected | PASS
15 | Click "Confirm" button | Login Page displayed | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 004 - Changing user's name, phone number, marketing preferences
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Ohm-Azing Components page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Menu button | Menu displayed | Worked as expected | PASS
3 | Click on Login | Login form displayed | Worked as expected | PASS
4 | Provide correct credentials and click login button | Landing Page Displayed | Worked as expected | PASS
|  | User Message Displayed | Worked as expected | PASS
5 | Click on Menu button | Menu displayed | Worked as expected | PASS
6 | Click on My Details | Prepopulated Personal Details displayed | Worked as expected | PASS
7 | Click on Profile Picture | File Input Displayed | Worked as expected | PASS
8 | Select picture | New Profile Picture Displayed | Worked as expected | PASS
5 | Change details in input fields | None | Worked as expected | PASS
6 | Click "Save Details" button | Landing Page Displayed | Worked as expected | PASS
|  | User Message Displayed | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 005 - Changing user's email
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Ohm-Azing Components page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Menu button | Menu displayed | Worked as expected | PASS
3 | Click on Login | Login form displayed | Worked as expected | PASS
4 | Provide correct credentials and click login button | Landing Page Displayed | Worked as expected | PASS
5 | Click on Menu button | Menu displayed | Worked as expected | PASS
6 | Click on My Details | Prepopulated My Details Page displayed | Worked as expected | PASS
7 | Scroll down to Account Settings | None | Worked as expected | PASS
8 | Click on Account Settings header | Account Settings displayed | Worked as expected | PASS
9 | Click on "Change Email" button | Email change form displayed | Worked as expected | PASS
10 | Don't provide any email | None | Worked as expected | PASS
11 | Click on "Add email" button | Error message "empty field" Displayed | Worked as expected | PASS
12 | Provide new email address | None | Worked as expected | PASS
13 | Click on "Add email" button | Provided email address appears in list as unverified | Worked as expected | PASS
Message displayed + verification email sent
14 | Select newly provided email address | None | Worked as expected | PASS
15 | Click on "Re-Send Verification" | Message displayed + verification email sent | Worked as expected | PASS
16 | Select newly provided email address | None | Worked as expected | PASS
17 | Click on "Remove" | Message displayed + email removed from list | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 006 - Changing user's password
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Ohm-Azing Components page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Menu button | Menu displayed | Worked as expected | PASS
3 | Click on Login | Login form displayed | Worked as expected | PASS
4 | Provide correct credentials and click login button | Landing Page Displayed | Worked as expected | PASS
5 | Click on Menu button | Menu displayed | Worked as expected | PASS
6 | Click on My Details | Prepopulated My Profile Form displayed | Worked as expected | PASS
7 | Scroll down to Account Settings | None | Worked as expected | PASS
8 | Click on Account Settings header | Account Settings displayed | Worked as expected | PASS
9 | Click on "Change Password" button | Password change form displayed | Worked as expected | PASS
10 | Don't provide any information | None | Worked as expected | PASS
11 | Click on "Change Password" button | Error message "empty field" Displayed | Worked as expected | PASS
12 | Provide old & new passwords (different) | None | Worked as expected | PASS
13 | Click on "Change Password" button | Error message "provide same passwrods" Displayed | Worked as expected | PASS
14 | Provide old & new passwords (same) | None | Worked as expected | PASS
15 | Click on "Change Password" button | Confirmation Message displayed | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 007 - Commenting on Shop Item
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Ohm-Azing Components page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Menu | Menu displayed | Worked as expected | PASS
3 | Click "Visit Shop" | Shop Page displayed | Worked as expected | PASS
4 | Select any category | Items options changed regrding selected category | Worked as expected | PASS
5 | Select an Item | Items detail displayed | Worked as expected | PASS
6 | Scroll down on the page | Comments of others displayed | Worked as expected | PASS
|  | Option for adding comment not displayed | Worked as expected | PASS
7 | Click on Menu button | Menu displayed | Worked as expected | PASS
8 | Click on Login | Login form displayed | Worked as expected | PASS
9 | Provide correct credentials and click login button | Landing Page Displayed | Worked as expected | PASS
10 | Click on Menu button | Menu displayed | Worked as expected | PASS
11 | Click "Visit Shop" | Shop Page displayed | Worked as expected | PASS
12 | Select any category | Items options changed regrding selected category | Worked as expected | PASS
13 | Select an Item | Items detail displayed | Worked as expected | PASS
14 | Scroll down on the page | Comments of others displayed | Worked as expected | PASS
|  | Input field for new comment displayed | Worked as expected | PASS
15 | Click on "Comment" button | Error message "empty field" Displayed | Worked as expected | PASS
16 | Provide new comment | None | Worked as expected | PASS
17 | Click on "Comment" button | "Pending approval" displayed | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 008 - Liking/Disliking on Shop Item
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Ohm-Azing Components page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Menu | Menu displayed | Worked as expected | PASS
3 | Click "Visit Shop" | Shop Page displayed | Worked as expected | PASS
4 | Select any category | Items options changed regrding selected category | Worked as expected | PASS
5 | Select an Item | Items detail displayed | Worked as expected | PASS
6 | See liking/disliking options under Item Name | Not visible (not logged in) | Worked as expected | PASS
7 | Click on Menu button | Menu displayed | Worked as expected | PASS
8 | Click on Login | Login form displayed | Worked as expected | PASS
9 | Provide correct credentials and click login button | Landing Page Displayed | Worked as expected | PASS
10 | Click on Menu button | Menu displayed | Worked as expected | PASS
11 | Click "Visit Shop" | Shop Page displayed | Worked as expected | PASS
12 | Select any category | Items options changed regrding selected category | Worked as expected | PASS
13 | Select an Item | Items detail displayed | Worked as expected | PASS
14 | See liking/disliking options under Item Name | Options visible | Worked as expected | PASS
15 | Click like button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Rating updated | Worked as expected | PASS
|  | Like button changed - toggle | Worked as expected | PASS
16 | Click like button again | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Rating updated | Worked as expected | PASS
|  | Like button changed - toggle | Worked as expected | PASS
17 | Click dislike button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Rating updated | Worked as expected | PASS
|  | Dislike button changed - toggle | Worked as expected | PASS
18 | Click dislike button again | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Rating updated | Worked as expected | PASS
|  | Dislike button changed - toggle | Worked as expected | PASS
19 | Click like button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Rating updated | Worked as expected | PASS
|  | Like button changed - toggle | Worked as expected | PASS
20 | Click dislike button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Rating updated | Worked as expected | PASS
|  | Like button changed - toggle | Worked as expected | PASS
|  | Dislike button changed - toggle | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 009 - Add to Wishlist
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Ohm-Azing Components page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Menu | Menu displayed | Worked as expected | PASS
3 | Click "Visit Shop" | Shop Page displayed | Worked as expected | PASS
4 | Select any category | Items options changed regrding selected category | Worked as expected | PASS
5 | Select an Item | Items detail displayed | Worked as expected | PASS
6 | See "Add to wishlist" under Item Name | Not visible (not logged in) | Worked as expected | PASS
7 | Click on Menu button | Menu displayed | Worked as expected | PASS
8 | Click on Login | Login form displayed | Worked as expected | PASS
9 | Provide correct credentials and click login button | Landing Page Displayed | Worked as expected | PASS
10 | Click on Menu button | Menu displayed | Worked as expected | PASS
11 | Click "Visit Shop" | Shop Page displayed | Worked as expected | PASS
12 | Select any category | Items options changed regrding selected category | Worked as expected | PASS
13 | Select an Item | Items detail displayed | Worked as expected | PASS
14 | See "Add to wishlist" under Item Name | Option visible | Worked as expected | PASS
15 | Click "Add to Wishlist" button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Bubble on Wishlist increased (appeared) | Worked as expected | PASS
|  | Wishlist button changed - toggle | Worked as expected | PASS
15 | Click "Remove from Wishlist" button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Bubble on Wishlist decreased (disappeared) | Worked as expected | PASS
|  | Wishlist button changed - toggle | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 010 - Wishlist functions
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Ohm-Azing Components page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Menu | Menu displayed | Worked as expected | PASS
3 | Click "Visit Shop" | Shop Page displayed | Worked as expected | PASS
4 | Select any category | Items options changed regrding selected category | Worked as expected | PASS
5 | Select an Item | Items detail displayed | Worked as expected | PASS
6 | See "Add to wishlist" under Item Name | Not visible (not logged in) | Worked as expected | PASS
7 | Click on Menu button | Menu displayed | Worked as expected | PASS
8 | Click on Login | Login form displayed | Worked as expected | PASS
9 | Provide correct credentials and click login button | Landing Page Displayed | Worked as expected | PASS
10 | Click on Menu button | Menu displayed | Worked as expected | PASS
11 | Click "Visit Shop" | Shop Page displayed | Worked as expected | PASS
12 | Select any category | Items options changed regrding selected category | Worked as expected | PASS
13 | Select an Item | Items detail displayed | Worked as expected | PASS
14 | See "Add to wishlist" under Item Name | Option visible | Worked as expected | PASS
15 | Click "Add to Wishlist" button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Bubble on Wishlist increased (appeared) | Worked as expected | PASS
|  | Wishlist button changed - toggle | Worked as expected | PASS
16 | Click on "Continue Shopping" button | Items options changed regrding selected category | Worked as expected | PASS
17 | Select another Item | Items detail displayed | Worked as expected | PASS
18 | Click "Add to Wishlist" button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Bubble on Wishlist increased | Worked as expected | PASS
|  | Wishlist button changed - toggle | Worked as expected | PASS
19 | Click on "Wishlist" in header | Wishlist Page displayed | Worked as expected | PASS
20 | Click "Remove" in Item row | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Item Removed | Worked as expected | PASS
21 | Click "Remove all items" button | Modal displayed | Worked as expected | PASS
22 | Click "Back" | Modal closes | Worked as expected | PASS
23 | Click "Remove all items" button | Modal displayed | Worked as expected | PASS
24 | Click "Clear Wishlist" button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Wishlist cleared | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 011 - Vault functions
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Ohm-Azing Components page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Menu | Menu displayed | Worked as expected | PASS
3 | Click "Visit Shop" | Shop Page displayed | Worked as expected | PASS
4 | Select any category | Items options changed regrding selected category | Worked as expected | PASS
5 | Select an Item | Items detail displayed | Worked as expected | PASS
6 | Click + button in quantity input | Quantity increses (up to available stock amount) | Worked as expected | PASS
7 | Click - button in quantity input | Quantity decreases (1 is being the lowest amount) | Worked as expected | PASS
8 | Click "Add to Vault" button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Bubble on Vault increased (appeared) | Worked as expected | PASS
9 | Click on "Continue Shopping" button | Items options changed regrding selected category | Worked as expected | PASS
10 | Select another Item | Items detail displayed | Worked as expected | PASS
11 | Click "Add to Vault" button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Bubble on Vault increased (appeared) | Worked as expected | PASS
12 | Click on "Vault" in header | Vault Page displayed | Worked as expected | PASS
13 | Click "Remove" in Item row | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Item Removed | Worked as expected | PASS
14 | Click + button in quantity input | Loader displayed | Worked as expected | PASS
|  | Quantity increses (up to available stock amount) | Worked as expected | PASS
15 | Click - button in quantity input | Loader displayed | Worked as expected | PASS
|  | Quantity decreases (1 is being the lowest amount) | Worked as expected | PASS
16 | Click "Remove all items" button | Modal displayed | Worked as expected | PASS
17 | Click "Back" | Modal closes | Worked as expected | PASS
18 | Click "Remove all items" button | Modal displayed | Worked as expected | PASS
19 | Click "Clear Vault" button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Vault Cleared | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 012 - Checkout functions
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | STEPS 1 - 12 OF TEST CASE 011 | Vault Page Displayed | Worked as expected | PASS
2 | Click on "Secure Checkout" button | Checkout Page displayed | Worked as expected | PASS
3 | Click on "Pay Now" button | Page scrolls up and highlights missing fields | Worked as expected | PASS
4 | Fill in all requested fields | None | Worked as expected | PASS
5 | Toggle delivery option | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Delivery option toggled | Worked as expected | PASS
6 | Click "Check Code" button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
7 | Enter "CI50" to Discount Code Field | None | Worked as expected | PASS
8 | Click "Check Code" button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Voucher details displayed | Worked as expected | PASS
9 | Click "Remove Voucher" button | Loader displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Voucher removed | Worked as expected | PASS
10 | Click on "Pay Now" button | Loader displayed | Worked as expected | PASS
|  | Card error message displayed | Worked as expected | PASS
11 | Ender Dummy Card details | None | Worked as expected | PASS
12 | Click "Pay Now" button | Loader displayed | Worked as expected | PASS
|  | Checkout Success Page displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS
|  | Invoice generated | Worked as expected | PASS
|  | Order saved into database | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 013 - Webhooks functions
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | STEPS 1 - 11 OF TEST CASE 012 | Vault Page Displayed | Worked as expected | PASS
2 | Click "Pay Now" button | Loader displayed | Worked as expected | PASS
3 | As soon as loader displayed close browser window | None | Worked as expected | PASS
4 | Webhook sent from Stripe | Invoice generated - WH on top | Worked as expected | PASS
|  | Confirmation email sent | Worked as expected | PASS
|  | Order saved into database | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 014 - Order History functions
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | STEPS 1 - 12 OF TEST CASE 012 | Order Saved into database | Worked as expected | PASS
2 | Click on Menu | Menu displayed | Worked as expected | PASS
3 | Click on "Order History" button | Not Available (Not logged in) | Worked as expected | PASS
4 | Click on Menu button | Menu displayed | Worked as expected | PASS
5 | Click on Login | Login form displayed | Worked as expected | PASS
6 | Provide correct credentials and click login button | Landing Page Displayed | Worked as expected | PASS
7 | Click on Menu button | Menu displayed | Worked as expected | PASS
8 | Click on "Order History" button | History Page Displayed | Worked as expected | PASS
9 | Click "View" button | Invoice opens in browser | Worked as expected | PASS
10 | Close the invoice | Back on "Order History" page | Worked as expected | PASS
11 | Click "Download" button | Invoice downloads | Worked as expected | PASS
PP5 Ohm-Azing Components
Test Case 015 - Deleting User account
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Ohm-Azing Components page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Menu button | Menu displayed | Worked as expected | PASS
3 | Click on Login | Login form displayed | Worked as expected | PASS
4 | Provide correct credentials and click login button | Landing Page Displayed | Worked as expected | PASS
5 | Click on Menu button | Menu displayed | Worked as expected | PASS
6 | Click on My Details | Prepopulated My Profile Form displayed | Worked as expected | PASS
7 | Scroll down to Account Cessation | None | Worked as expected | PASS
8 | Click on "Delete Account" button | Modal displays | Worked as expected | PASS
9 | Click "Back" | Modal closes | Worked as expected | PASS
10 | Click on "Delete Account" button | Modal displays | Worked as expected | PASS
11 | Click "Delete My Account" button | Landing Page Displayed | Worked as expected | PASS
|  | Message displayed | Worked as expected | PASS

## PEP8 testing
Directory | File | Result
\checkout | admin.py | PASS
\checkout | forms.py | PASS
\checkout | models.py | PASS
\checkout | urls.py | PASS
\checkout | views.py | PASS
\checkout | webhook_handler.py | PASS
\checkout | webhooks.py | PASS
\history | urls.py | PASS
\history | views.py | PASS
\items | admin.py | PASS
\items | forms.py | PASS
\items | models.py | PASS
\items | urls.py | PASS
\items | views.py | PASS
\landing | urls.py | PASS
\landing | views.py | PASS
\ohmazing-components | asgi.py | PASS
\ohmazing-components | settings.py | FAIL *( Appendix XX )*
\ohmazing-components | urls.py | PASS
\ohmazing-components | wsgi.py | PASS
\owner | admin.py | PASS
\owner | forms.py | PASS
\owner | models.py | PASS
\owner | urls.py | PASS
\owner | views.py | PASS
\owner | widgets.py | PASS
\profilemanager | admin.py | PASS
\profilemanager | forms.py | PASS
\profilemanager | models.py | PASS
\profilemanager | urls.py | PASS
\profilemanager | views.py | PASS
\vault | context_list.py | PASS
\vault | urls.py | PASS
\vault | views.py | PASS
\wishlist | context_list.py | PASS
\wishlist | urls.py | PASS
\wishlist | views.py | PASS
\ | custom_storages.py | PASS

## JS testing
Directory | File | Result
\static\js | checkout.js | PASS
\static\js | easter_egg.js | PASS
\static\js | product_detail.js | PASS
\static\js | profile_picture.js | PASS
\static\js | register.js | PASS
\static\js | stripe_elements.js | PASS
\static\js | vault.js | PASS
\static\js | wishlist.js | PASS

## CSS Validation
Directory | File | Warnings | Errors | Nature of Problem | Result
\static\css | checkout.css | 33 | 0 | Dynamic - can't be checked statically | PASS
\static\css | error.css | 4 | 0 | Dynamic - can't be checked statically | PASS
\static\css | footer.css | 7 | 0 | Dynamic - can't be checked statically | PASS
\static\css | header.css | 15 | 0 | Dynamic - can't be checked statically | PASS
\static\css | history.css | 6 | 0 | Dynamic - can't be checked statically | PASS
\static\css | items.css | 44 | 0 | Dynamic - can't be checked statically | PASS
\static\css | landing.css | 21 | 0 | Dynamic - can't be checked statically | PASS
\static\css | main.css | 25 | 0 | Dynamic - can't be checked statically | PASS
\static\css | owner.css | 23 | 0 | Dynamic - can't be checked statically | PASS
\static\css | profilemanager.css | 14 | 0 | Dynamic - can't be checked statically | PASS
\static\css | search.css | 13 | 0 | Dynamic - can't be checked statically | PASS
\static\css | wishlist_vault.css | 11 | 0 | Dynamic - can't be checked statically | PASS

## VAWE Validation
Directory | File | State | Alerts | Errors | Nature of Problem | Result
\checkout | checkout_ok.html | Not Applicable | 1 | 0 | Orphaned form | PASS
\checkout | checkout.html | Not Applicable | 1 | 0 | Redundant link | PASS
\history | order_history.html | Only Logged in | 4 | 0 | Table caption | PASS
\items | item_detail.html | Logged In | 1 | 0 | Missing H1 | PASS
|  | Not Logged In | 1 | 0 | Missing H1 | PASS
\items | shop.html | Not Applicable | 3 | 0 | Select label, missing H1 | PASS
\landing | index.html | Not Applicable | 1 | 0 | Missing H1 | PASS
\landing | search_results.html | Not Applicable | 0 | 0 |  | PASS
\owner | categories.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | category_delete_confirm.html | Only as SuperUser | 1 | 0 | Redundant link | PASS
\owner | comment_delete_confirm.html | Only as SuperUser | 1 | 0 | Redundant link | PASS
\owner | comments_owner.html | Only as SuperUser | 3 | 0 | Select label, table caption | PASS
\owner | edit_category.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | edit_email.html | Only as SuperUser | 1 | 0 | Small text (CK Editor) | PASS
\owner | edit_item.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | edit_voucher.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | email_delete_confirm.html | Only as SuperUser | 1 | 0 | Redundant link | PASS
\owner | invoices.html | Only as SuperUser | 3 | 0 | Select label, table caption | PASS
\owner | item_delete_confirm.html | Only as SuperUser | 1 | 0 | Redundant link | PASS
\owner | items.html | Only as SuperUser | 3 | 0 | Select label, table caption | PASS
\owner | new_category.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | new_email.html | Only as SuperUser | 1 | 0 | Small text (CK Editor) | PASS
\owner | new_item.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | new_voucher.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | newsletter_emails.html | Only as SuperUser | 3 | 0 | Select label, table caption | PASS
\owner | owner.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | postage.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | voucher_delete_confirm.html | Only as SuperUser | 1 | 0 | Redundant link | PASS
\owner | vouchers.html | Only as SuperUser | 3 | 0 | Select label, table caption | PASS
\profilemanager | my_details.html | Only Logged in | 0 | 0 |  | PASS
\vault | vault.html | Not Applicable | 1 | 0 | Redundant link | PASS
\wishlist | wishlist.html | Only Logged in | 1 | 0 | Redundant link | PASS
\templates | 403.html | Not Applicable | 0 | 0 |  | PASS
\templates | 404.html | Not Applicable | 0 | 0 |  | PASS
\templates | 500.html | Not Applicable | 0 | 0 |  | PASS
\templates | base.html | Not Applicable | 0 | 0 |  | PASS
\templates | footer.html | Not Applicable | 0 | 0 |  | PASS
\templates | header.html | Logged In | 2 | 0 | Small text (if items in vault and wishlist) | PASS
\templates | header.html | Not Logged In | 2 | 0 | Small text (if items in vault and wishlist) | PASS
\templates\toasts | toast_error.html | Not Applicable | 0 | 0 |  | PASS
\templates\toasts | toast_info.html | Not Applicable | 0 | 0 |  | PASS
\templates\toasts | toast_success.html | Not Applicable | 0 | 0 |  | PASS
\templates\toasts | toast_vault.html | Not Applicable | 0 | 0 |  | PASS

## HTML Validation
Directory | File | State | Warnings | Errors | Nature of Problem | Result
\checkout | checkout_ok.html | Not Applicable | 0 | 0 |  | PASS
\checkout | checkout.html | Not Applicable | 0 | 0 |  | PASS
\history | order_history.html | Only Logged in | 0 | 0 |  | PASS
\items | item_detail.html | Logged In | 0 | 0 |  | PASS
|  | Not Logged In | 0 | 0 |  | PASS
\items | shop.html | Not Applicable | 0 | 0 |  | PASS
\landing | index.html | Not Applicable | 0 | 0 |  | PASS
\landing | search_results.html | Not Applicable | 0 | 0 |  | PASS
\owner | categories.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | category_delete_confirm.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | comment_delete_confirm.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | comments_owner.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | edit_category.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | edit_email.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | edit_item.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | edit_voucher.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | email_delete_confirm.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | invoices.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | item_delete_confirm.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | items.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | new_category.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | new_email.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | new_item.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | new_voucher.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | newsletter_emails.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | owner.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | postage.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | voucher_delete_confirm.html | Only as SuperUser | 0 | 0 |  | PASS
\owner | vouchers.html | Only as SuperUser | 0 | 0 |  | PASS
\profilemanager | my_details.html | Only Logged in | 0 | 0 |  | PASS
\vault | vault.html | Not Applicable | 0 | 0 |  | PASS
\wishlist | wishlist.html | Only Logged in | 0 | 0 |  | PASS
\templates | 403.html | Not Applicable | 0 | 0 |  | PASS
\templates | 404.html | Not Applicable | 0 | 0 |  | PASS
\templates | 500.html | Not Applicable | 0 | 0 |  | PASS
\templates | base.html | Not Applicable | 0 | 0 |  | PASS
\templates | footer.html | Not Applicable | 0 | 0 |  | PASS
\templates | header.html | Logged In | 0 | 0 |  | PASS
\templates | header.html | Not Logged In | 0 | 0 |  | PASS
\templates\toasts | toast_error.html | Not Applicable | 0 | 0 |  | PASS
\templates\toasts | toast_info.html | Not Applicable | 0 | 0 |  | PASS
\templates\toasts | toast_success.html | Not Applicable | 0 | 0 |  | PASS
\templates\toasts | toast_vault.html | Not Applicable | 0 | 0 |  | PASS

## Bugs
Issue | Title | Description | Screenshot | Solution | Final Commit | Result
[# 82](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/82) | BUG : Compatibility issue popper.js vs bootstrap.js | Combination of popper.js and bootstrap.min.js libraries preventing modals to open. When popper.js changed to newer version, then dropdown menu not opening. | N/A | Changed separate files `popper.js` and `bootstrap.min.js` to one file `bootstrap.bundle.min.js`. | [ee66e4f](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/ee66e4fe7c19df3697b47ac897fdde5791871cba) | FIXED
[# 83](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/83) | BUG : Console error - toasts | Error regarding toasts apperas when ladning page is loaded. | N/A | Created if else statement in `base.hmtl` to only show toast only if there is any available. | [4a52421](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/4a52421c6f41145589b4f7e32a176266fb7c450e) | FIXED
[# 84](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/84) | BUG : Date Time Compare - Vouchers - Admin tools | Error visible in the terminal window when section Vouchers in Admin Tools is accessed. | *Attachement* | Changed `DateTimeField` to `DateField` in Newsletter model and add sorting of Vouchers inside of `views.py`. | [bb1963e](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/bb1963efedec3c771f59b2d4eed81db0ee6793d8) | FIXED
[# 85](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/85) | BUG : Admin tools - emails - 400 http response | Admin tools - Emails - returns 400 HTTP response when deployed. | N/A | TinyMCE editor replaced by CKEditor. | [bde7c57](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/bde7c576add1b28f046458401dfbad0ed4dea654) | FIXED
[# 86](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/86) | BUG : Overflowing header icons | Icons are sticking out of header on devices with height < 800px. | N/A | Set fixed height of all header elements in class `.header-height` | [caa5de1](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/caa5de161cd73ad30702eeafe9e2a78f287440cb) | FIXED
[# 87](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/87) | BUG : Items with no sizes not adding to Vault | Items that has no sizes are not adding to Vault from the Item Detail page. | N/A | Changed default size in checkout `views.py` from `size = request.POST.get('size', 0)` to `size = request.POST.get('size', 1)`. This ensures correct multiplication of sub-methods. | [e960cf0](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/e960cf041e5212d63353994bfeae5007db79e79d) | FIXED
[# 88](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/88) | BUG : Unresponsive "Continue Shopping" link | Continue Shopping button malfunctioning when shop item accessed from elsewhere than Shop page. | N/A | JS script deleted, static link to shop used instead. | [afa6f55](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/afa6f552a71f02b00573f05a7664a16cd7ecedba) | FIXED
[# 89](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/89) | BUG : Non digit quantity field submission - vault | It is possible to submit non-digit quantity field value and site throws 500 error. | N/A | `if new_quantity.isdigit():` used in post method of `views.py` in vault app | [f90e353](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/f90e353901b79ed1e8083944ebcbf61716692e1d) | FIXED
[# 90](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/90) | BUG : Zero stock amount item - adding to Vault | It is possible to add item that's not in stock to Vault. | N/A | Quantity adding input field and "Add to Vault" button displayed only if item is in stock, `{% if item.item_stock > 0 %}` added to `item_detail.html` template. | [28df137](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/28df137429572fad923d9e487e81cd9afd1a8295) | FIXED
[# 91](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/91) | BUG : Hidden toasts stacking on top of each other | Vault toasts are stacking on top of each other in Y axle even if the previous toasts are hidden. | *Attachement* | Line `$('.toast:not(:first-child)').remove();` added to `base.html` template into block of toasts JS logic. This ensures all previous toastes are cleared before new one attached. | [6db5a0a](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/6db5a0a97cd21c93c3ad6a3aebdc508a5a93064e) | FIXED
[# 92](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/92) | BUG : Stripe minimum order amount | Stripe payment intent cannot be created if the amount to charge is < 0.50 €. | *Attachement* | Minimum order value added to postage settings model and line `elif subtotal < postage_settings.minimum_order:` added to checkout `views.py`. | [e4af873](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/e4af873f36a2d1aa30d69d5f2248e6a4fbd67efc) | FIXED
[# 93](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/93) | BUG : Amount of likes/dislikes not displaying correctly | The amount of likes / dislikes isn't counted properly when initial shop page opened. | N/A | Anottation of likes and dislikes added to initial access of shop page. | [e6ff664](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/e6ff66447bf172cf0ad2e4133b8566445efcfc5b) | FIXED
[# 94](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/94) | BUG : Delivery option changed - toast not displaying properly | Error message "Payment cannot be processed" appears after changing delivery option changed. | N/A | Line `if request.POST.get('payment-checker') == 'true' and order_form.is_valid():` split into two separate statements with different else outputs. | [d67a354](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/d67a354ed23b1436a47d8bc2339fdfa3d4e19406) | FIXED
[# 95](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/95) | BUG : Property "scale" not valid - W3C | Property "scale" throws W3C validator error. | N/A | Property `scale: x` was replaced by `transform: scale(x)`. | [d2f8a5a](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/d2f8a5af34e5447385796a73a270ea102f2314d0) | FIXED
[# 96](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/issues/96) | BUG : Header of emails covered by logo | Header of email is covered by logo in New Order and Newsletter emails on desktop devices. | *Attachement* | Paragraph with inline styling added as first to the email. `<p style="color: #fafafa; margin-top: 10vh;">` | [6d7ec46](https://github.com/tomik-z-cech/PP5-Ohm-Azing-Components/commit/6d7ec46ae11ebc0d05a15acf23164a435b24f66b) | FIXED